## Sheet1
Meeting title | further planning meeting
Date | 2023-10-06 | Meeting Time | 11:00PM-12:30PM | Meeting Location | WZ11
Type of meeting |  | Discuss client feedback on project progress and next steps.
Note taker |  | Penelope Huang 18032371
Reviewer |  | Tang Yu 18015903
Mentor |  | Stephen Thorpe
Client |  | Ramesh Lal
Attendees |  | Penelope Huang, Tang Yu, Stephen Thorpe
Topic | Project investigation progress and direction
Discussion | After discussing the information provided with the client with the mentor, the group had a clearer plan. We need to provide a solution to move these nervous systems. Therefore We need to understand what's going on. This system can helps manage client relationships, projects and leads more efficiently and provides a centralized platform for coordinating collaborations and promotional activities. The current report did not meet the client's needs and the mentor requested that we conduct a meeting with the stakeholder of the management system. He send requests to client and stakeholder.
Agenda | Stakeholder meeting Agenda: 1. what she does 2. what she thinks the current problems are 3. what she would like the new system to do.
Action Items | Stakeholder Meeting | Person responsible | All | Deadline
Action Items | State Report | Person responsible | All | Deadline | 2023-10-13
Next Step | Get in touch with beneficiaries and schedule meetings. Prepare to submit status report