## Sheet1
Meeting title | further planning meeting
Date | 202310/10 | Meeting Time | 16:00PM-18:00PM | Meeting Location | WZ1124
Type of meeting |  | Show and Confirm
Note taker |  | Penelope Huang 18032371
Reviewer |  | Tang Yu 18015903
Mentor |  | Stephen Thorpe
Client |  | Ramesh Lal
Attendees |  | Penelope Huang, Tang Yu, Ramesh Lal
Topic | Show work results and keep pace with client
Discussion | We presented our work results and discussed the deviations between the project scope and the client's expectations. In this meeting, we learned that what we did was somewhat different from what the client expected. We were in the wrong direction in terms of the project scope and high level requirement
Conclusions | Update project scope
Action Items | Project Scope and Project Proposal | Person responsible | All | Deadline | Week 11
Next Step | Write a new project scope for the client to confirm and update our project proposal