## Sheet1
Issue Register
Issue | Issue Description | Type | Date Reported | Priority(M/H/L) | Status | Comments
1 | What is the rational for the project -what is it's reason for existing | Project Proposals | 2023-10-02 | M | Complete
2 | need reqirement for report 1& 2 | Project Proposals | 2023-10-02 | H | Complete
3 | Missing rationale and justification in Skills analysis | Project Proposals | 2023-10-02 | M | Complete
4 | Wrong Project management methodology (Scrum doesn’t help) | Project Proposals | 2023-10-02 | H | Complete
5 | Role of Team member | Project Proposals | 2023-10-02 | M | Complete
6 | Appendix 1-Algorithms | Project Proposals | 2023-10-02 | L | Complete
7 | Skill Analysis( need business logic) | Project Proposals | 2023-10-09 | M | Complete
8 | Add more Functional Reguirements | Project Proposals | 2023-10-11 | L | Complete
9 | Report 1 and 2 should More specific to beneficiaries and links to existing systems | System report | 2023-10-14 | M
10 | Makeup a Project Scope Statement | Project Proposals | 2023-10-14 | H | Complete
1 | Unclear requirements | Project Proposals | 2023-11-07 | H | Complete
2 | PMI scheme role | Project Proposals | 2023-11-07 | M | Complete
3 | Risk reigister | Project Proposals | 2023-11-07 | H | Complete
4 | Issues register | Project Proposals | 2023-11-07 | H | Complete
5 | WBS | Project proposals | 2023-11-07 | H |  | Update Gantt chart and WBS diagram
6 | budget control | Portfolio | 2023-11-07 | M | Complete
7 | Missing Project quality and Planning | Portfolio | 2023-11-07 | H | Complete
8 | Group meeting and individual records | Portfolio | 2023-11-07 | L